## AutoReshore 1S-2R
SHORING AND RESHORING ANALYSIS - ACI SP-4 METHOD - AutoReshore 1S-2R
Version 1.1
INPUTS
| Form sets |  | 1 |  | Reshore sets |  | 2
| Shore spacing |  |  |  | Reshore spacing |  |  | Analysis ID
| N-S | 5 |  |  | N-S | 5 |  | 2014-10-01
| E-W | 5 |  |  | E-W | 5
| Area | 25 |  |  | Area | 25
[5 empty] | Load Factor | Area Load
| Fresh slab weight |  |  |  | 1 | 1 | 1
| Cured slab weight |  |  |  | 1 | 1 | 1
| Form/shore weight |  |  |  | 1 | 0.1 | 0.1
| Construction live load |  |  |  | 1 | 0.5 | 0.5
| Reshore weight |  |  |  | 1 | 0.05 | 0.05
Step # | Slab # | Load carried by slab |  |  | Unit load carried by shore | [5 empty] | Total individual shore load
|  | beginning | chg dur | end |  | end of operation |  |  |  |  | end of operation
1 - A | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Place 1st floor slab
[6 empty] | 1.6 |  |  |  |  | 40
1 - B | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
1 - C | 1 | 0 | 1 | 1 |  |  |  |  | 1 | Remove 1st floor shores
[6 empty] | 0 |  |  |  |  | 0
1 - D | 1 | 1 | 0 | 1 |  |  |  |  | 1 | Place 1st floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
2 - A | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Place 2nd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.65 |  |  |  |  | 41.25
2 - B | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.15 |  |  |  |  | 28.75
2 - C | 2 | 0 | 1 | 1 |  |  |  |  | 2 | Remove 2nd floor shores
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.05 |  |  |  |  | 1.25
2 - D | 2 | 1 | 0 | 1 |  |  |  |  | 2 | Place 2nd floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.1 |  |  |  |  | 2.5
3 - A | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Place 3rd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 1.65 |  |  |  |  | 41.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.7 |  |  |  |  | 42.5
3 - B | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 1.15 |  |  |  |  | 28.75
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.2 |  |  |  |  | 30
3 - C | 3 | 0 | 1 | 1 |  |  |  |  | 3 | Remove 3rd floor shores
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.1 |  |  |  |  | 2.5
3 - D | 3 | 1 | 0 | 1 |  |  |  |  | 3 | Remove 1st floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0.05 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
3 - E | 3 | 1 | 0 | 1 |  |  |  |  | 3 | Place 3rd floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1 | 0.025 | 1.025 |  |  |  |  | 2
[6 empty] | 0.075 |  |  |  |  | 1.875
| 1 | 1.05 | 0.025 | 1.075 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - A | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Place 4th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 3 | 1 | 0.53333 | 1.5333 |  |  |  |  | 3
[6 empty] | 1.1167 |  |  |  |  | 27.9167
| 2 | 1.025 | 0.53333 | 1.5583 |  |  |  |  | 2
[6 empty] | 0.60833 |  |  |  |  | 15.2083
| 1 | 1.075 | 0.53333 | 1.6083 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - B | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 3 | 1.5333 | -0.16667 | 1.3667 |  |  |  |  | 3
[6 empty] | 0.78333 |  |  |  |  | 19.5833
| 2 | 1.5583 | -0.16667 | 1.3917 |  |  |  |  | 2
[6 empty] | 0.44167 |  |  |  |  | 11.0417
| 1 | 1.6083 | -0.16667 | 1.4417 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - C | 4 | 0 | 1 | 1 |  |  |  |  | 4 | Remove 4th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1.3667 | -0.36667 | 1 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.3917 | -0.34167 | 1.05 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1.4417 | -0.39167 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - D | 4 | 1 | 0 | 1 |  |  |  |  | 4 | Remove 2nd floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1.05 | -0.05 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - E | 4 | 1 | 0 | 1 |  |  |  |  | 4 | Place 4th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1 | 0.025 | 1.025 |  |  |  |  | 3
[6 empty] | 0.075 |  |  |  |  | 1.875
| 2 | 1.05 | 0.025 | 1.075 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - A | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Place 5th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 4 | 1 | 0.53333 | 1.5333 |  |  |  |  | 4
[6 empty] | 1.1167 |  |  |  |  | 27.9167
| 3 | 1.025 | 0.53333 | 1.5583 |  |  |  |  | 3
[6 empty] | 0.60833 |  |  |  |  | 15.2083
| 2 | 1.075 | 0.53333 | 1.6083 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - B | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 4 | 1.5333 | -0.16667 | 1.3667 |  |  |  |  | 4
[6 empty] | 0.78333 |  |  |  |  | 19.5833
| 3 | 1.5583 | -0.16667 | 1.3917 |  |  |  |  | 3
[6 empty] | 0.44167 |  |  |  |  | 11.0417
| 2 | 1.6083 | -0.16667 | 1.4417 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - C | 5 | 0 | 1 | 1 |  |  |  |  | 5 | Remove 5th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.3667 | -0.36667 | 1 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.3917 | -0.34167 | 1.05 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.4417 | -0.39167 | 1.05 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - D | 5 | 1 | 0 | 1 |  |  |  |  | 5 | Remove 3rd floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.05 | 0 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1.05 | -0.05 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - E | 5 | 1 | 0 | 1 |  |  |  |  | 5 | Place 5th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1 | 0.025 | 1.025 |  |  |  |  | 4
[6 empty] | 0.075 |  |  |  |  | 1.875
| 3 | 1.05 | 0.025 | 1.075 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
6 - A | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Place 6th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 5 | 1 | 0.53333 | 1.5333 |  |  |  |  | 5
[6 empty] | 1.1167 |  |  |  |  | 27.9167
| 4 | 1.025 | 0.53333 | 1.5583 |  |  |  |  | 4
[6 empty] | 0.60833 |  |  |  |  | 15.2083
| 3 | 1.075 | 0.53333 | 1.6083 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - B | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 5 | 1.5333 | -0.16667 | 1.3667 |  |  |  |  | 5
[6 empty] | 0.78333 |  |  |  |  | 19.5833
| 4 | 1.5583 | -0.16667 | 1.3917 |  |  |  |  | 4
[6 empty] | 0.44167 |  |  |  |  | 11.0417
| 3 | 1.6083 | -0.16667 | 1.4417 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - C | 6 | 0 | 1 | 1 |  |  |  |  | 6 | Remove 6th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.3667 | -0.36667 | 1 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.3917 | -0.34167 | 1.05 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.4417 | -0.39167 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - D | 6 | 1 | 0 | 1 |  |  |  |  | 6 | Remove 4th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.05 | 0 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1.05 | -0.05 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - E | 6 | 1 | 0 | 1 |  |  |  |  | 6 | Place 6th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1 | 0.025 | 1.025 |  |  |  |  | 5
[6 empty] | 0.075 |  |  |  |  | 1.875
| 4 | 1.05 | 0.025 | 1.075 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
7 - A | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Place 7th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 6 | 1 | 0.53333 | 1.5333 |  |  |  |  | 6
[6 empty] | 1.1167 |  |  |  |  | 27.9167
| 5 | 1.025 | 0.53333 | 1.5583 |  |  |  |  | 5
[6 empty] | 0.60833 |  |  |  |  | 15.2083
| 4 | 1.075 | 0.53333 | 1.6083 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - B | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 6 | 1.5333 | -0.16667 | 1.3667 |  |  |  |  | 6
[6 empty] | 0.78333 |  |  |  |  | 19.5833
| 5 | 1.5583 | -0.16667 | 1.3917 |  |  |  |  | 5
[6 empty] | 0.44167 |  |  |  |  | 11.0417
| 4 | 1.6083 | -0.16667 | 1.4417 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - C | 7 | 0 | 1 | 1 |  |  |  |  | 7 | Remove 7th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.3667 | -0.36667 | 1 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.3917 | -0.34167 | 1.05 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.4417 | -0.39167 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - D | 7 | 1 | 0 | 1 |  |  |  |  | 7 | Remove 5th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.05 | 0 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.05 | -0.05 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - E | 7 | 1 | 0 | 1 |  |  |  |  | 7 | Place 7th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1 | 0.025 | 1.025 |  |  |  |  | 6
[6 empty] | 0.075 |  |  |  |  | 1.875
| 5 | 1.05 | 0.025 | 1.075 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
8 - A | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Place 8th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 7 | 1 | 0.53333 | 1.5333 |  |  |  |  | 7
[6 empty] | 1.1167 |  |  |  |  | 27.9167
| 6 | 1.025 | 0.53333 | 1.5583 |  |  |  |  | 6
[6 empty] | 0.60833 |  |  |  |  | 15.2083
| 5 | 1.075 | 0.53333 | 1.6083 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - B | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 7 | 1.5333 | -0.16667 | 1.3667 |  |  |  |  | 7
[6 empty] | 0.78333 |  |  |  |  | 19.5833
| 6 | 1.5583 | -0.16667 | 1.3917 |  |  |  |  | 6
[6 empty] | 0.44167 |  |  |  |  | 11.0417
| 5 | 1.6083 | -0.16667 | 1.4417 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - C | 8 | 0 | 1 | 1 |  |  |  |  | 8 | Remove 8th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.3667 | -0.36667 | 1 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.3917 | -0.34167 | 1.05 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.4417 | -0.39167 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - D | 8 | 1 | 0 | 1 |  |  |  |  | 8 | Remove 6th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.05 | 0 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.05 | -0.05 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - E | 8 | 1 | 0 | 1 |  |  |  |  | 8 | Place 8th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1 | 0.025 | 1.025 |  |  |  |  | 7
[6 empty] | 0.075 |  |  |  |  | 1.875
| 6 | 1.05 | 0.025 | 1.075 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
9 - A | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Place 9th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 8 | 1 | 0.53333 | 1.5333 |  |  |  |  | 8
[6 empty] | 1.1167 |  |  |  |  | 27.9167
| 7 | 1.025 | 0.53333 | 1.5583 |  |  |  |  | 7
[6 empty] | 0.60833 |  |  |  |  | 15.2083
| 6 | 1.075 | 0.53333 | 1.6083 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - B | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 8 | 1.5333 | -0.16667 | 1.3667 |  |  |  |  | 8
[6 empty] | 0.78333 |  |  |  |  | 19.5833
| 7 | 1.5583 | -0.16667 | 1.3917 |  |  |  |  | 7
[6 empty] | 0.44167 |  |  |  |  | 11.0417
| 6 | 1.6083 | -0.16667 | 1.4417 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - C | 9 | 0 | 1 | 1 |  |  |  |  | 9 | Remove 9th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1.3667 | -0.36667 | 1 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.3917 | -0.34167 | 1.05 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.4417 | -0.39167 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - D | 9 | 1 | 0 | 1 |  |  |  |  | 9 | Remove 7th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1 | 0 | 1 |  |  |  |  | 8
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.05 | 0 | 1.05 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.05 | -0.05 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - E | 9 | 1 | 0 | 1 |  |  |  |  | 9 | Place 9th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1 | 0.025 | 1.025 |  |  |  |  | 8
[6 empty] | 0.075 |  |  |  |  | 1.875
| 7 | 1.05 | 0.025 | 1.075 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
10 - A | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Place 10th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 9 | 1 | 0.53333 | 1.5333 |  |  |  |  | 9
[6 empty] | 1.1167 |  |  |  |  | 27.9167
| 8 | 1.025 | 0.53333 | 1.5583 |  |  |  |  | 8
[6 empty] | 0.60833 |  |  |  |  | 15.2083
| 7 | 1.075 | 0.53333 | 1.6083 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - B | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 9 | 1.5333 | -0.16667 | 1.3667 |  |  |  |  | 9
[6 empty] | 0.78333 |  |  |  |  | 19.5833
| 8 | 1.5583 | -0.16667 | 1.3917 |  |  |  |  | 8
[6 empty] | 0.44167 |  |  |  |  | 11.0417
| 7 | 1.6083 | -0.16667 | 1.4417 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - C | 10 | 0 | 1 | 1 |  |  |  |  | 10 | Remove 10th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1.3667 | -0.36667 | 1 |  |  |  |  | 9
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1.3917 | -0.34167 | 1.05 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.4417 | -0.39167 | 1.05 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - D | 10 | 1 | 0 | 1 |  |  |  |  | 10 | Remove 8th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1 | 0 | 1 |  |  |  |  | 9
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1.05 | 0 | 1.05 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.05 | -0.05 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - E | 10 | 1 | 0 | 1 |  |  |  |  | 10 | Remove 10th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1 | 0 | 1 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1.05 | -0.05 | 1 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0

## AutoReshore 1S-3R
SHORING AND RESHORING ANALYSIS - ACI SP-4 METHOD - AutoReshore 1S-3R
Version 1.1
INPUTS
| Form sets |  | 1 |  | Reshore sets |  | 3
| Shore spacing |  |  |  | Reshore spacing |  |  | Analysis ID
| N-S | 5 |  |  | N-S | 5 |  | 2014-10-01
| E-W | 5 |  |  | E-W | 5
| Area | 25 |  |  | Area | 25
[5 empty] | Load Factor | Area Load
| Fresh slab weight |  |  |  | 1 | 1 | 1
| Cured slab weight |  |  |  | 1 | 1 | 1
| Form/shore weight |  |  |  | 1 | 0.1 | 0.1
| Construction live load |  |  |  | 1 | 0.5 | 0.5
| Reshore weight |  |  |  | 1 | 0.05 | 0.05
Step # | Slab # | Load carried by slab |  |  | Unit load carried by shore | [5 empty] | Total individual shore load
|  | beginning | chg dur | end |  | end of operation |  |  |  |  | end of operation
1 - A | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Place 1st floor slab
[6 empty] | 1.6 |  |  |  |  | 40
1 - B | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
1 - C | 1 | 0 | 1 | 1 |  |  |  |  | 1 | Remove shore
[6 empty] | 0 |  |  |  |  | 0
1 - D | 1 | 1 | 0 | 1 |  |  |  |  | 1 | Place 1st floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
2 - A | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Place 2nd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.65 |  |  |  |  | 41.25
2 - B | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.15 |  |  |  |  | 28.75
2 - C | 2 | 0 | 1 | 1 |  |  |  |  | 2 | Remove shore
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.05 |  |  |  |  | 1.25
2 - D | 2 | 1 | 0 | 1 |  |  |  |  | 2 | Place 2nd floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.1 |  |  |  |  | 2.5
3 - A | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Place 3rd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 1.65 |  |  |  |  | 41.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.7 |  |  |  |  | 42.5
3 - B | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 1.15 |  |  |  |  | 28.75
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.2 |  |  |  |  | 30
3 - C | 3 | 0 | 1 | 1 |  |  |  |  | 3 | Remove 3rd floor shores
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.1 |  |  |  |  | 2.5
3 - D | 3 | 1 | 0 | 1 |  |  |  |  | 3 | Place 3rd floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0.1 |  |  |  |  | 2.5
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.15 |  |  |  |  | 3.75
4 - A | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Place 4th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 1.65 |  |  |  |  | 41.25
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 1.7 |  |  |  |  | 42.5
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.75 |  |  |  |  | 43.75
4 - B | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 1.15 |  |  |  |  | 28.75
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 1.2 |  |  |  |  | 30
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.25 |  |  |  |  | 31.25
4 - C | 4 | 0 | 1 | 1 |  |  |  |  | 4 | Remove 4th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0.1 |  |  |  |  | 2.5
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.15 |  |  |  |  | 3.75
4 - D | 4 | 1 | 0 | 1 |  |  |  |  | 4 | Remove 1st floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1 | 0.05 | 1.05 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0.05 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - E | 4 | 1 | 0 | 1 |  |  |  |  | 4 | Place 4th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1 | 0.016667 | 1.0167 |  |  |  |  | 3
[6 empty] | 0.083333 |  |  |  |  | 2.0833
| 2 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 2
[6 empty] | 0.066667 |  |  |  |  | 1.6667
| 1 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - A | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Place 5th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 4 | 1 | 0.4 | 1.4 |  |  |  |  | 4
[6 empty] | 1.25 |  |  |  |  | 31.25
| 3 | 1.0167 | 0.4 | 1.4167 |  |  |  |  | 3
[6 empty] | 0.88333 |  |  |  |  | 22.0833
| 2 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 2
[6 empty] | 0.46667 |  |  |  |  | 11.6667
| 1 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - B | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 4 | 1.4 | -0.125 | 1.275 |  |  |  |  | 4
[6 empty] | 0.875 |  |  |  |  | 21.875
| 3 | 1.4167 | -0.125 | 1.2917 |  |  |  |  | 3
[6 empty] | 0.63333 |  |  |  |  | 15.8333
| 2 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 2
[6 empty] | 0.34167 |  |  |  |  | 8.5417
| 1 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - C | 5 | 0 | 1 | 1 |  |  |  |  | 5 | Remove 5th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.275 | -0.275 | 1 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.2917 | -0.24167 | 1.05 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - D | 5 | 1 | 0 | 1 |  |  |  |  | 5 | Remove 2nd floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.05 | 0 | 1.05 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1.05 | -0.05 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - E | 5 | 1 | 0 | 1 |  |  |  |  | 5 | Place 5th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1 | 0.016667 | 1.0167 |  |  |  |  | 4
[6 empty] | 0.083333 |  |  |  |  | 2.0833
| 3 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 3
[6 empty] | 0.066667 |  |  |  |  | 1.6667
| 2 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
6 - A | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Place 6th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 5 | 1 | 0.4 | 1.4 |  |  |  |  | 5
[6 empty] | 1.25 |  |  |  |  | 31.25
| 4 | 1.0167 | 0.4 | 1.4167 |  |  |  |  | 4
[6 empty] | 0.88333 |  |  |  |  | 22.0833
| 3 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 3
[6 empty] | 0.46667 |  |  |  |  | 11.6667
| 2 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - B | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 5 | 1.4 | -0.125 | 1.275 |  |  |  |  | 5
[6 empty] | 0.875 |  |  |  |  | 21.875
| 4 | 1.4167 | -0.125 | 1.2917 |  |  |  |  | 4
[6 empty] | 0.63333 |  |  |  |  | 15.8333
| 3 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 3
[6 empty] | 0.34167 |  |  |  |  | 8.5417
| 2 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - C | 6 | 0 | 1 | 1 |  |  |  |  | 6 | Remove 6th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.275 | -0.275 | 1 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.2917 | -0.24167 | 1.05 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - D | 6 | 1 | 0 | 1 |  |  |  |  | 6 | Remove 3th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.05 | 0 | 1.05 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.05 | 0 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1.05 | -0.05 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - E | 6 | 1 | 0 | 1 |  |  |  |  | 6 | Place 6th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1 | 0.016667 | 1.0167 |  |  |  |  | 5
[6 empty] | 0.083333 |  |  |  |  | 2.0833
| 4 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 4
[6 empty] | 0.066667 |  |  |  |  | 1.6667
| 3 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
7 - A | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Place 7th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 6 | 1 | 0.4 | 1.4 |  |  |  |  | 6
[6 empty] | 1.25 |  |  |  |  | 31.25
| 5 | 1.0167 | 0.4 | 1.4167 |  |  |  |  | 5
[6 empty] | 0.88333 |  |  |  |  | 22.0833
| 4 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 4
[6 empty] | 0.46667 |  |  |  |  | 11.6667
| 3 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - B | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 6 | 1.4 | -0.125 | 1.275 |  |  |  |  | 6
[6 empty] | 0.875 |  |  |  |  | 21.875
| 5 | 1.4167 | -0.125 | 1.2917 |  |  |  |  | 5
[6 empty] | 0.63333 |  |  |  |  | 15.8333
| 4 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 4
[6 empty] | 0.34167 |  |  |  |  | 8.5417
| 3 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - C | 7 | 0 | 1 | 1 |  |  |  |  | 7 | Remove 7th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.275 | -0.275 | 1 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.2917 | -0.24167 | 1.05 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - D | 7 | 1 | 0 | 1 |  |  |  |  | 7 | Remove 4th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.05 | 0 | 1.05 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.05 | 0 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1.05 | -0.05 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - E | 7 | 1 | 0 | 1 |  |  |  |  | 7 | Place 7th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1 | 0.016667 | 1.0167 |  |  |  |  | 6
[6 empty] | 0.083333 |  |  |  |  | 2.0833
| 5 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 5
[6 empty] | 0.066667 |  |  |  |  | 1.6667
| 4 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
8 - A | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Place 8th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 7 | 1 | 0.4 | 1.4 |  |  |  |  | 7
[6 empty] | 1.25 |  |  |  |  | 31.25
| 6 | 1.0167 | 0.4 | 1.4167 |  |  |  |  | 6
[6 empty] | 0.88333 |  |  |  |  | 22.0833
| 5 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 5
[6 empty] | 0.46667 |  |  |  |  | 11.6667
| 4 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - B | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 7 | 1.4 | -0.125 | 1.275 |  |  |  |  | 7
[6 empty] | 0.875 |  |  |  |  | 21.875
| 6 | 1.4167 | -0.125 | 1.2917 |  |  |  |  | 6
[6 empty] | 0.63333 |  |  |  |  | 15.8333
| 5 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 5
[6 empty] | 0.34167 |  |  |  |  | 8.5417
| 4 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - C | 8 | 0 | 1 | 1 |  |  |  |  | 8 | Remove 8th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.275 | -0.275 | 1 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.2917 | -0.24167 | 1.05 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - D | 8 | 1 | 0 | 1 |  |  |  |  | 8 | Remove 5th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.05 | 0 | 1.05 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.05 | 0 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.05 | -0.05 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - E | 8 | 1 | 0 | 1 |  |  |  |  | 8 | Place 8th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1 | 0.016667 | 1.0167 |  |  |  |  | 7
[6 empty] | 0.083333 |  |  |  |  | 2.0833
| 6 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 6
[6 empty] | 0.066667 |  |  |  |  | 1.6667
| 5 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
9 - A | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Place 9th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 8 | 1 | 0.4 | 1.4 |  |  |  |  | 8
[6 empty] | 1.25 |  |  |  |  | 31.25
| 7 | 1.0167 | 0.4 | 1.4167 |  |  |  |  | 7
[6 empty] | 0.88333 |  |  |  |  | 22.0833
| 6 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 6
[6 empty] | 0.46667 |  |  |  |  | 11.6667
| 5 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - B | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 8 | 1.4 | -0.125 | 1.275 |  |  |  |  | 8
[6 empty] | 0.875 |  |  |  |  | 21.875
| 7 | 1.4167 | -0.125 | 1.2917 |  |  |  |  | 7
[6 empty] | 0.63333 |  |  |  |  | 15.8333
| 6 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 6
[6 empty] | 0.34167 |  |  |  |  | 8.5417
| 5 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - C | 9 | 0 | 1 | 1 |  |  |  |  | 9 | Remove 9th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1.275 | -0.275 | 1 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.2917 | -0.24167 | 1.05 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - D | 9 | 1 | 0 | 1 |  |  |  |  | 9 | Remove 6th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1 | 0 | 1 |  |  |  |  | 8
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.05 | 0 | 1.05 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.05 | 0 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.05 | -0.05 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - E | 9 | 1 | 0 | 1 |  |  |  |  | 9 | Place 9th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1 | 0.016667 | 1.0167 |  |  |  |  | 8
[6 empty] | 0.083333 |  |  |  |  | 2.0833
| 7 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 7
[6 empty] | 0.066667 |  |  |  |  | 1.6667
| 6 | 1.05 | 0.016667 | 1.0667 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
10 - A | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Place 10th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 9 | 1 | 0.4 | 1.4 |  |  |  |  | 9
[6 empty] | 1.25 |  |  |  |  | 31.25
| 8 | 1.0167 | 0.4 | 1.4167 |  |  |  |  | 8
[6 empty] | 0.88333 |  |  |  |  | 22.0833
| 7 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 7
[6 empty] | 0.46667 |  |  |  |  | 11.6667
| 6 | 1.0667 | 0.4 | 1.4667 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - B | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 9 | 1.4 | -0.125 | 1.275 |  |  |  |  | 9
[6 empty] | 0.875 |  |  |  |  | 21.875
| 8 | 1.4167 | -0.125 | 1.2917 |  |  |  |  | 8
[6 empty] | 0.63333 |  |  |  |  | 15.8333
| 7 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 7
[6 empty] | 0.34167 |  |  |  |  | 8.5417
| 6 | 1.4667 | -0.125 | 1.3417 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - C | 10 | 0 | 1 | 1 |  |  |  |  | 10 | Remove 10th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1.275 | -0.275 | 1 |  |  |  |  | 9
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1.2917 | -0.24167 | 1.05 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.3417 | -0.29167 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - D | 10 | 1 | 0 | 1 |  |  |  |  | 10 | Remove 7th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1 | 0 | 1 |  |  |  |  | 9
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1.05 | 0 | 1.05 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.05 | 0 | 1.05 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.05 | -0.05 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - E | 10 | 1 | 0 | 1 |  |  |  |  | 10 | Remove 8th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1 | 0 | 1 |  |  |  |  | 9
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1.05 | 0 | 1.05 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.05 | -0.05 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - F | 10 | 1 | 0 | 1 |  |  |  |  | 10 | Remove 10th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1 | 0 | 1 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1.05 | -0.05 | 1 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0

## AutoReshore 2S-1R
SHORING AND RESHORING ANALYSIS - ACI SP-4 METHOD - AutoReshore 2S-1R
Version 1.1
INPUTS
| Form sets |  | 2 |  | Reshore sets |  | 1
| Shore spacing |  |  |  | Reshore spacing |  |  | Analysis ID
| N-S | 5 |  |  | N-S | 5 |  | 2014-10-01
| E-W | 5 |  |  | E-W | 5
| Area | 25 |  |  | Area | 25
[5 empty] | Load Factor | Area Load
| Fresh slab weight |  |  |  | 1 | 1 | 1
| Cured slab weight |  |  |  | 1 | 1 | 1
| Form/shore weight |  |  |  | 1 | 0.1 | 0.1
| Construction live load |  |  |  | 1 | 0.5 | 0.5
| Reshore weight |  |  |  | 1 | 0.05 | 0.05
Step # | Slab # | Load carried by slab |  |  | Unit load carried by shore | [5 empty] | Total individual shore load
|  | beginning | chg dur | end |  | end of operation |  |  |  |  | end of operation
1 - A | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Place 1st floor slab
[6 empty] | 1.6 |  |  |  |  | 40
1 - B | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
2 - A | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Place 2nd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 1 | 0 | 0 | 0 |  |  |  |  | 1
[6 empty] | 2.7 |  |  |  |  | 67.5
2 - B | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 1 | 0 | 0 | 0 |  |  |  |  | 1
[6 empty] | 2.2 |  |  |  |  | 55
2 - C | 2 | 0 | 1.05 | 1.05 |  |  |  |  | 2 | Remove 1st floor shore
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 0 | 1.05 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
2 - D | 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2 | Place 1st floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 0.05 |  |  |  |  | 1.25
3 - A | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Place 3rd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2
[6 empty] | 1.65 |  |  |  |  | 41.25
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 1.65 |  |  |  |  | 41.25
3 - B | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2
[6 empty] | 1.15 |  |  |  |  | 28.75
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 1.15 |  |  |  |  | 28.75
3 - C | 3 | 0 | 0.525 | 0.525 |  |  |  |  | 3 | Remove 2nd floor shores
[6 empty] | 0.575 |  |  |  |  | 14.375
| 2 | 1.05 | 0.525 | 1.575 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1.05 | -0.05 | 1 |  |  |  |  | 1
[6 empty] | 0.05 |  |  |  |  | 1.25
3 - D | 3 | 0.525 | 0 | 0.525 |  |  |  |  | 3 | Remove 1st floor reshores
[6 empty] | 0.575 |  |  |  |  | 14.375
| 2 | 1.575 | 0 | 1.575 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
3 - E | 3 | 0.525 | 0 | 0.525 |  |  |  |  | 3 | Place 2nd floor reshores
[6 empty] | 0.575 |  |  |  |  | 14.375
| 2 | 1.575 | 0 | 1.575 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0.05 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - A | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Place 4th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 3 | 0.525 | 0.53333 | 1.0583 |  |  |  |  | 3
[6 empty] | 1.6417 |  |  |  |  | 41.0417
| 2 | 1.575 | 0.53333 | 2.1083 |  |  |  |  | 2
[6 empty] | 0.58333 |  |  |  |  | 14.5833
| 1 | 1.05 | 0.53333 | 1.5833 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - B | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 3 | 1.0583 | -0.16667 | 0.89167 |  |  |  |  | 3
[6 empty] | 1.3083 |  |  |  |  | 32.7083
| 2 | 2.1083 | -0.16667 | 1.9417 |  |  |  |  | 2
[6 empty] | 0.41667 |  |  |  |  | 10.4167
| 1 | 1.5833 | -0.16667 | 1.4167 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - C | 4 | 0 | 0.60417 | 0.60417 |  |  |  |  | 4 | Remove 3rd floor shores
[6 empty] | 0.49583 |  |  |  |  | 12.3958
| 3 | 0.89167 | 0.60417 | 1.4958 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1.9417 | -0.94167 | 1 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1.4167 | -0.36667 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - D | 4 | 0.60417 | 0 | 0.60417 |  |  |  |  | 4 | Remove 2nd floor reshores
[6 empty] | 0.49583 |  |  |  |  | 12.3958
| 3 | 1.4958 | 0 | 1.4958 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1.05 | -0.05 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - E | 4 | 0.60417 | 0 | 0.60417 |  |  |  |  | 4 | Place 3rd floor reshores
[6 empty] | 0.49583 |  |  |  |  | 12.3958
| 3 | 1.4958 | 0 | 1.4958 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1 | 0.05 | 1.05 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - A | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Place 5th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 4 | 0.60417 | 0.53333 | 1.1375 |  |  |  |  | 4
[6 empty] | 1.5625 |  |  |  |  | 39.0625
| 3 | 1.4958 | 0.53333 | 2.0292 |  |  |  |  | 3
[6 empty] | 0.58333 |  |  |  |  | 14.5833
| 2 | 1.05 | 0.53333 | 1.5833 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - B | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 4 | 1.1375 | -0.16667 | 0.97083 |  |  |  |  | 4
[6 empty] | 1.2292 |  |  |  |  | 30.7292
| 3 | 2.0292 | -0.16667 | 1.8625 |  |  |  |  | 3
[6 empty] | 0.41667 |  |  |  |  | 10.4167
| 2 | 1.5833 | -0.16667 | 1.4167 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - C | 5 | 0 | 0.56458 | 0.56458 |  |  |  |  | 5 | Remove 4th floor shores
[6 empty] | 0.53542 |  |  |  |  | 13.3854
| 4 | 0.97083 | 0.56458 | 1.5354 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1.8625 | -0.8625 | 1 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.4167 | -0.36667 | 1.05 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - D | 5 | 0.56458 | 0 | 0.56458 |  |  |  |  | 5 | Remove 3rd floor reshores
[6 empty] | 0.53542 |  |  |  |  | 13.3854
| 4 | 1.5354 | 0 | 1.5354 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1.05 | -0.05 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - E | 5 | 0.56458 | 0 | 0.56458 |  |  |  |  | 5 | Place 4th floor reshores
[6 empty] | 0.53542 |  |  |  |  | 13.3854
| 4 | 1.5354 | 0 | 1.5354 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1 | 0.05 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
6 - A | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Place 6th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 5 | 0.56458 | 0.53333 | 1.0979 |  |  |  |  | 5
[6 empty] | 1.6021 |  |  |  |  | 40.0521
| 4 | 1.5354 | 0.53333 | 2.0688 |  |  |  |  | 4
[6 empty] | 0.58333 |  |  |  |  | 14.5833
| 3 | 1.05 | 0.53333 | 1.5833 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - B | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 5 | 1.0979 | -0.16667 | 0.93125 |  |  |  |  | 5
[6 empty] | 1.2688 |  |  |  |  | 31.7188
| 4 | 2.0688 | -0.16667 | 1.9021 |  |  |  |  | 4
[6 empty] | 0.41667 |  |  |  |  | 10.4167
| 3 | 1.5833 | -0.16667 | 1.4167 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - C | 6 | 0 | 0.58437 | 0.58437 |  |  |  |  | 6 | Remove 5th floor shores
[6 empty] | 0.51562 |  |  |  |  | 12.8906
| 5 | 0.93125 | 0.58437 | 1.5156 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.9021 | -0.90208 | 1 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.4167 | -0.36667 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - D | 6 | 0.58437 | 0 | 0.58437 |  |  |  |  | 6 | Remove 4th floor reshores
[6 empty] | 0.51562 |  |  |  |  | 12.8906
| 5 | 1.5156 | 0 | 1.5156 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1.05 | -0.05 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - E | 6 | 0.58437 | 0 | 0.58437 |  |  |  |  | 6 | Place 5th floor reshores
[6 empty] | 0.51562 |  |  |  |  | 12.8906
| 5 | 1.5156 | 0 | 1.5156 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1 | 0.05 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
7 - A | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Place 7th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 6 | 0.58437 | 0.53333 | 1.1177 |  |  |  |  | 6
[6 empty] | 1.5823 |  |  |  |  | 39.5573
| 5 | 1.5156 | 0.53333 | 2.049 |  |  |  |  | 5
[6 empty] | 0.58333 |  |  |  |  | 14.5833
| 4 | 1.05 | 0.53333 | 1.5833 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - B | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 6 | 1.1177 | -0.16667 | 0.95104 |  |  |  |  | 6
[6 empty] | 1.249 |  |  |  |  | 31.224
| 5 | 2.049 | -0.16667 | 1.8823 |  |  |  |  | 5
[6 empty] | 0.41667 |  |  |  |  | 10.4167
| 4 | 1.5833 | -0.16667 | 1.4167 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - C | 7 | 0 | 0.57448 | 0.57448 |  |  |  |  | 7 | Remove 6th floor shores
[6 empty] | 0.52552 |  |  |  |  | 13.138
| 6 | 0.95104 | 0.57448 | 1.5255 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.8823 | -0.88229 | 1 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.4167 | -0.36667 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - D | 7 | 0.57448 | 0 | 0.57448 |  |  |  |  | 7 | Remove 5th floor reshores
[6 empty] | 0.52552 |  |  |  |  | 13.138
| 6 | 1.5255 | 0 | 1.5255 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.05 | -0.05 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - E | 7 | 0.57448 | 0 | 0.57448 |  |  |  |  | 7 | Place 6th floor reshores
[6 empty] | 0.52552 |  |  |  |  | 13.138
| 6 | 1.5255 | 0 | 1.5255 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1 | 0.05 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
8 - A | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Place 8th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 7 | 0.57448 | 0.53333 | 1.1078 |  |  |  |  | 7
[6 empty] | 1.5922 |  |  |  |  | 39.8047
| 6 | 1.5255 | 0.53333 | 2.0589 |  |  |  |  | 6
[6 empty] | 0.58333 |  |  |  |  | 14.5833
| 5 | 1.05 | 0.53333 | 1.5833 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - B | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 7 | 1.1078 | -0.16667 | 0.94115 |  |  |  |  | 7
[6 empty] | 1.2589 |  |  |  |  | 31.4714
| 6 | 2.0589 | -0.16667 | 1.8922 |  |  |  |  | 6
[6 empty] | 0.41667 |  |  |  |  | 10.4167
| 5 | 1.5833 | -0.16667 | 1.4167 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - C | 8 | 0 | 0.57943 | 0.57943 |  |  |  |  | 8 | Remove 7th floor shores
[6 empty] | 0.52057 |  |  |  |  | 13.0143
| 7 | 0.94115 | 0.57943 | 1.5206 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.8922 | -0.89219 | 1 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.4167 | -0.36667 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - D | 8 | 0.57943 | 0 | 0.57943 |  |  |  |  | 8 | Remove 6th floor reshores
[6 empty] | 0.52057 |  |  |  |  | 13.0143
| 7 | 1.5206 | 0 | 1.5206 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.05 | -0.05 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - E | 8 | 0.57943 | 0 | 0.57943 |  |  |  |  | 8 | Place 7th floor reshores
[6 empty] | 0.52057 |  |  |  |  | 13.0143
| 7 | 1.5206 | 0 | 1.5206 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1 | 0.05 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
9 - A | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Place 9th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 8 | 0.57943 | 0.53333 | 1.1128 |  |  |  |  | 8
[6 empty] | 1.5872 |  |  |  |  | 39.681
| 7 | 1.5206 | 0.53333 | 2.0539 |  |  |  |  | 7
[6 empty] | 0.58333 |  |  |  |  | 14.5833
| 6 | 1.05 | 0.53333 | 1.5833 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - B | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 8 | 1.1128 | -0.16667 | 0.94609 |  |  |  |  | 8
[6 empty] | 1.2539 |  |  |  |  | 31.3477
| 7 | 2.0539 | -0.16667 | 1.8872 |  |  |  |  | 7
[6 empty] | 0.41667 |  |  |  |  | 10.4167
| 6 | 1.5833 | -0.16667 | 1.4167 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - C | 9 | 0 | 0.57695 | 0.57695 |  |  |  |  | 9 | Remove 8th floor shores
[6 empty] | 0.52305 |  |  |  |  | 13.0762
| 8 | 0.94609 | 0.57695 | 1.523 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.8872 | -0.88724 | 1 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.4167 | -0.36667 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - D | 9 | 0.57695 | 0 | 0.57695 |  |  |  |  | 9 | Remove 7th floor reshores
[6 empty] | 0.52305 |  |  |  |  | 13.0762
| 8 | 1.523 | 0 | 1.523 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.05 | -0.05 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - E | 9 | 0.57695 | 0 | 0.57695 |  |  |  |  | 9 | Place 8th floor reshores
[6 empty] | 0.52305 |  |  |  |  | 13.0762
| 8 | 1.523 | 0 | 1.523 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1 | 0.05 | 1.05 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
10 - A | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Place 10th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 9 | 0.57695 | 0.53333 | 1.1103 |  |  |  |  | 9
[6 empty] | 1.5897 |  |  |  |  | 39.7428
| 8 | 1.523 | 0.53333 | 2.0564 |  |  |  |  | 8
[6 empty] | 0.58333 |  |  |  |  | 14.5833
| 7 | 1.05 | 0.53333 | 1.5833 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - B | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 9 | 1.1103 | -0.16667 | 0.94362 |  |  |  |  | 9
[6 empty] | 1.2564 |  |  |  |  | 31.4095
| 8 | 2.0564 | -0.16667 | 1.8897 |  |  |  |  | 8
[6 empty] | 0.41667 |  |  |  |  | 10.4167
| 7 | 1.5833 | -0.16667 | 1.4167 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - C | 10 | 0 | 0.57819 | 0.57819 |  |  |  |  | 10 | Remove 9th floor shores
[6 empty] | 0.52181 |  |  |  |  | 13.0452
| 9 | 0.94362 | 0.57819 | 1.5218 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1.8897 | -0.88971 | 1 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.4167 | -0.36667 | 1.05 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - D | 10 | 0.57819 | 0 | 0.57819 |  |  |  |  | 10 | Remove 8th floor reshores
[6 empty] | 0.52181 |  |  |  |  | 13.0452
| 9 | 1.5218 | 0 | 1.5218 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1 | 0 | 1 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.05 | -0.05 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - E | 10 | 0.57819 | 0.42181 | 1 |  |  |  |  | 10 | Remove 10th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1.5218 | -0.52181 | 1 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1 | 0 | 1 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0

## AutoReshore 2S-2R
SHORING AND RESHORING ANALYSIS - ACI SP-4 METHOD - AutoReshore 2S-2R
Version 1.1
INPUT
| Form sets |  | 2 |  | Reshore sets |  | 2
| Shore spacing |  |  |  | Reshore spacing |  |  | Analysis ID
| N-S | 5 |  |  | N-S | 5 |  | 2014-10-01
| E-W | 5 |  |  | E-W | 5
| Area | 25 |  |  | Area | 25
[5 empty] | Load Factor | Area Load
| Fresh slab weight |  |  |  | 1 | 1 | 1
| Cured slab weight |  |  |  | 1 | 1 | 1
| Form/shore weight |  |  |  | 1 | 0.1 | 0.1
| Construction live load |  |  |  | 1 | 0.5 | 0.5
| Reshore weight |  |  |  | 1 | 0.05 | 0.05
Step # | Slab # | Load carried by slab |  |  | Unit load carried by shore | [5 empty] | Total individual shore load
|  | beginning | chg dur | end |  | end of operation |  |  |  |  | end of operation
1 - A | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Place 1st floor slab
[6 empty] | 1.6 |  |  |  |  | 40
1 - B | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
2 - A | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Place 2nd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 1 | 0 | 0 | 0 |  |  |  |  | 1
[6 empty] | 2.7 |  |  |  |  | 67.5
2 - B | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 1 | 0 | 0 | 0 |  |  |  |  | 1
[6 empty] | 2.2 |  |  |  |  | 55
2 - C | 2 | 0 | 1.05 | 1.05 |  |  |  |  | 2 | Remove 1st floor shores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 0 | 1.05 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
2 - D | 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2 | Place 1st floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 0.05 |  |  |  |  | 1.25
3 - A | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Place 3rd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2
[6 empty] | 1.65 |  |  |  |  | 41.25
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 1.65 |  |  |  |  | 41.25
3 - B | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2
[6 empty] | 1.15 |  |  |  |  | 28.75
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 1.15 |  |  |  |  | 28.75
3 - C | 3 | 0 | 0.525 | 0.525 |  |  |  |  | 3 | Remove 2nd floor shores
[6 empty] | 0.575 |  |  |  |  | 14.375
| 2 | 1.05 | 0.525 | 1.575 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1.05 | -0.05 | 1 |  |  |  |  | 1
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
3 - D | 3 | 0.525 | 0 | 0.525 |  |  |  |  | 3 | Place 2nd floor reshores
[6 empty] | 0.575 |  |  |  |  | 14.375
| 2 | 1.575 | 0 | 1.575 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.1 |  |  |  |  | 2.5
4 - A | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Place 4th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 3 | 0.525 | 0 | 0.525 |  |  |  |  | 3
[6 empty] | 2.175 |  |  |  |  | 54.375
| 2 | 1.575 | 0 | 1.575 |  |  |  |  | 2
[6 empty] | 1.65 |  |  |  |  | 41.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.7 |  |  |  |  | 42.5
4 - B | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 3 | 0.525 | 0 | 0.525 |  |  |  |  | 3
[6 empty] | 1.675 |  |  |  |  | 41.875
| 2 | 1.575 | 0 | 1.575 |  |  |  |  | 2
[6 empty] | 1.15 |  |  |  |  | 28.75
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 1.2 |  |  |  |  | 30
4 - C | 4 | 0 | 0.7875 | 0.7875 |  |  |  |  | 4 | Remove 3rd floor shores
[6 empty] | 0.3125 |  |  |  |  | 7.8125
| 3 | 0.525 | 0.7875 | 1.3125 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1.575 | -0.575 | 1 |  |  |  |  | 2
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0.1 |  |  |  |  | 2.5
4 - D | 4 | 0.7875 | 0 | 0.7875 |  |  |  |  | 4 | Remove !st floor reshores
[6 empty] | 0.3125 |  |  |  |  | 7.8125
| 3 | 1.3125 | 0 | 1.3125 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1 | 0.05 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - E | 4 | 0.7875 | 0 | 0.7875 |  |  |  |  | 4 | Place 3rd floor reshores
[6 empty] | 0.3125 |  |  |  |  | 7.8125
| 3 | 1.3125 | 0 | 1.3125 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1 | 0.025 | 1.025 |  |  |  |  | 2
[6 empty] | 0.075 |  |  |  |  | 1.875
| 1 | 1.05 | 0.025 | 1.075 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - A | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Place 5th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 4 | 0.7875 | 0.4 | 1.1875 |  |  |  |  | 4
[6 empty] | 1.5125 |  |  |  |  | 37.8125
| 3 | 1.3125 | 0.4 | 1.7125 |  |  |  |  | 3
[6 empty] | 0.85 |  |  |  |  | 21.25
| 2 | 1.025 | 0.4 | 1.425 |  |  |  |  | 2
[6 empty] | 0.475 |  |  |  |  | 11.875
| 1 | 1.075 | 0.4 | 1.475 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - B | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 4 | 1.1875 | -0.125 | 1.0625 |  |  |  |  | 4
[6 empty] | 1.1375 |  |  |  |  | 28.4375
| 3 | 1.7125 | -0.125 | 1.5875 |  |  |  |  | 3
[6 empty] | 0.6 |  |  |  |  | 15
| 2 | 1.425 | -0.125 | 1.3 |  |  |  |  | 2
[6 empty] | 0.35 |  |  |  |  | 8.75
| 1 | 1.475 | -0.125 | 1.35 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - C | 5 | 0 | 0.51875 | 0.51875 |  |  |  |  | 5 | Remove 4th floor shores
[6 empty] | 0.58125 |  |  |  |  | 14.5312
| 4 | 1.0625 | 0.51875 | 1.5813 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1.5875 | -0.5875 | 1 |  |  |  |  | 3
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.3 | -0.25 | 1.05 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1.35 | -0.3 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - D | 5 | 0.51875 | 0 | 0.51875 |  |  |  |  | 5 | Remove 2nd floor reshores
[6 empty] | 0.58125 |  |  |  |  | 14.5312
| 4 | 1.5813 | 0 | 1.5813 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.05 | 0 | 1.05 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1.05 | -0.05 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - E | 5 | 0.51875 | 0 | 0.51875 |  |  |  |  | 5 | Place 4th floor reshores
[6 empty] | 0.58125 |  |  |  |  | 14.5312
| 4 | 1.5813 | 0 | 1.5813 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1 | 0.025 | 1.025 |  |  |  |  | 3
[6 empty] | 0.075 |  |  |  |  | 1.875
| 2 | 1.05 | 0.025 | 1.075 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
6 - A | 6 | 0 | 0 | 0 |  |  |  |  | 5 | Place 6th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 5 | 0.51875 | 0.4 | 0.91875 |  |  |  |  | 4
[6 empty] | 1.7812 |  |  |  |  | 44.5312
| 4 | 1.5813 | 0.4 | 1.9812 |  |  |  |  | 3
[6 empty] | 0.85 |  |  |  |  | 21.25
| 3 | 1.025 | 0.4 | 1.425 |  |  |  |  | 2
[6 empty] | 0.475 |  |  |  |  | 11.875
| 2 | 1.075 | 0.4 | 1.475 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
6 - B | 6 | 0 | 0 | 0 |  |  |  |  | 5 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 5 | 0.91875 | -0.125 | 0.79375 |  |  |  |  | 4
[6 empty] | 1.4062 |  |  |  |  | 35.1562
| 4 | 1.9812 | -0.125 | 1.8562 |  |  |  |  | 3
[6 empty] | 0.6 |  |  |  |  | 15
| 3 | 1.425 | -0.125 | 1.3 |  |  |  |  | 2
[6 empty] | 0.35 |  |  |  |  | 8.75
| 2 | 1.475 | -0.125 | 1.35 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
6 - C | 6 | 0 | 0.65312 | 0.65312 |  |  |  |  | 5 | Remove 4th floor shores
[6 empty] | 0.44688 |  |  |  |  | 11.1719
| 5 | 0.79375 | 0.65312 | 1.4469 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.8562 | -0.85625 | 1 |  |  |  |  | 3
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.3 | -0.25 | 1.05 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.35 | -0.3 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
6 - D | 6 | 0.65312 | 0 | 0.65312 |  |  |  |  | 6 | Remove 3rd floor reshores
[6 empty] | 0.44688 |  |  |  |  | 11.1719
| 5 | 1.4469 | 0 | 1.4469 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.05 | 0 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1.05 | -0.05 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - E | 6 | 0.65312 | 0 | 0.65312 |  |  |  |  | 6 | Place 5th floor reshores
[6 empty] | 0.44688 |  |  |  |  | 11.1719
| 5 | 1.4469 | 0 | 1.4469 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1 | 0.025 | 1.025 |  |  |  |  | 4
[6 empty] | 0.075 |  |  |  |  | 1.875
| 3 | 1.05 | 0.025 | 1.075 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
7 - A | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Place 7th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 6 | 0.65312 | 0.4 | 1.0531 |  |  |  |  | 6
[6 empty] | 1.6469 |  |  |  |  | 41.1719
| 5 | 1.4469 | 0.4 | 1.8469 |  |  |  |  | 5
[6 empty] | 0.85 |  |  |  |  | 21.25
| 4 | 1.025 | 0.4 | 1.425 |  |  |  |  | 4
[6 empty] | 0.475 |  |  |  |  | 11.875
| 3 | 1.075 | 0.4 | 1.475 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - B | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 6 | 1.0531 | -0.125 | 0.92812 |  |  |  |  | 6
[6 empty] | 1.2719 |  |  |  |  | 31.7969
| 5 | 1.8469 | -0.125 | 1.7219 |  |  |  |  | 5
[6 empty] | 0.6 |  |  |  |  | 15
| 4 | 1.425 | -0.125 | 1.3 |  |  |  |  | 4
[6 empty] | 0.35 |  |  |  |  | 8.75
| 3 | 1.475 | -0.125 | 1.35 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - C | 7 | 0 | 0.58594 | 0.58594 |  |  |  |  | 7 | Remove 6th floor shores
[6 empty] | 0.51406 |  |  |  |  | 12.8516
| 6 | 0.92812 | 0.58594 | 1.5141 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.7219 | -0.72188 | 1 |  |  |  |  | 5
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.3 | -0.25 | 1.05 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.35 | -0.3 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - D | 7 | 0.58594 | 0 | 0.58594 |  |  |  |  | 7 | Remove 4th floor reshores
[6 empty] | 0.51406 |  |  |  |  | 12.8516
| 6 | 1.5141 | 0 | 1.5141 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.05 | 0 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1.05 | -0.05 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - E | 7 | 0.58594 | 0 | 0.58594 |  |  |  |  | 7 | Place 6th floor reshores
[6 empty] | 0.51406 |  |  |  |  | 12.8516
| 6 | 1.5141 | 0 | 1.5141 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1 | 0.025 | 1.025 |  |  |  |  | 5
[6 empty] | 0.075 |  |  |  |  | 1.875
| 4 | 1.05 | 0.025 | 1.075 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
8 - A | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Place 8th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 7 | 0.58594 | 0.4 | 0.98594 |  |  |  |  | 7
[6 empty] | 1.7141 |  |  |  |  | 42.8516
| 6 | 1.5141 | 0.4 | 1.9141 |  |  |  |  | 6
[6 empty] | 0.85 |  |  |  |  | 21.25
| 5 | 1.025 | 0.4 | 1.425 |  |  |  |  | 5
[6 empty] | 0.475 |  |  |  |  | 11.875
| 4 | 1.075 | 0.4 | 1.475 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - B | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 7 | 0.98594 | -0.125 | 0.86094 |  |  |  |  | 7
[6 empty] | 1.3391 |  |  |  |  | 33.4766
| 6 | 1.9141 | -0.125 | 1.7891 |  |  |  |  | 6
[6 empty] | 0.6 |  |  |  |  | 15
| 5 | 1.425 | -0.125 | 1.3 |  |  |  |  | 5
[6 empty] | 0.35 |  |  |  |  | 8.75
| 4 | 1.475 | -0.125 | 1.35 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - C | 8 | 0 | 0.61953 | 0.61953 |  |  |  |  | 8 | Remove 7th floor shores
[6 empty] | 0.48047 |  |  |  |  | 12.0117
| 7 | 0.86094 | 0.61953 | 1.4805 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.7891 | -0.78906 | 1 |  |  |  |  | 6
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.3 | -0.25 | 1.05 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.35 | -0.3 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - D | 8 | 0.61953 | 0 | 0.61953 |  |  |  |  | 8 | Remove 5th floor reshores
[6 empty] | 0.48047 |  |  |  |  | 12.0117
| 7 | 1.4805 | 0 | 1.4805 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.05 | 0 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.05 | -0.05 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - E | 8 | 0.61953 | 0 | 0.61953 |  |  |  |  | 8 | Place 7th floor reshores
[6 empty] | 0.48047 |  |  |  |  | 12.0117
| 7 | 1.4805 | 0 | 1.4805 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1 | 0.025 | 1.025 |  |  |  |  | 6
[6 empty] | 0.075 |  |  |  |  | 1.875
| 5 | 1.05 | 0.025 | 1.075 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
9 - A | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Place 9th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 8 | 0.61953 | 0.4 | 1.0195 |  |  |  |  | 8
[6 empty] | 1.6805 |  |  |  |  | 42.0117
| 7 | 1.4805 | 0.4 | 1.8805 |  |  |  |  | 7
[6 empty] | 0.85 |  |  |  |  | 21.25
| 6 | 1.025 | 0.4 | 1.425 |  |  |  |  | 6
[6 empty] | 0.475 |  |  |  |  | 11.875
| 5 | 1.075 | 0.4 | 1.475 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - B | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 8 | 1.0195 | -0.125 | 0.89453 |  |  |  |  | 8
[6 empty] | 1.3055 |  |  |  |  | 32.6367
| 7 | 1.8805 | -0.125 | 1.7555 |  |  |  |  | 7
[6 empty] | 0.6 |  |  |  |  | 15
| 6 | 1.425 | -0.125 | 1.3 |  |  |  |  | 6
[6 empty] | 0.35 |  |  |  |  | 8.75
| 5 | 1.475 | -0.125 | 1.35 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - C | 9 | 0 | 0.60273 | 0.60273 |  |  |  |  | 9 | Remove 8th floor shores
[6 empty] | 0.49727 |  |  |  |  | 12.4316
| 8 | 0.89453 | 0.60273 | 1.4973 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.7555 | -0.75547 | 1 |  |  |  |  | 7
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.3 | -0.25 | 1.05 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.35 | -0.3 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - D | 9 | 0.60273 | 0 | 0.60273 |  |  |  |  | 9 | Remove 6th floor reshores
[6 empty] | 0.49727 |  |  |  |  | 12.4316
| 8 | 1.4973 | 0 | 1.4973 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.05 | 0 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.05 | -0.05 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - E | 9 | 0.60273 | 0 | 0.60273 |  |  |  |  | 9 | Place 8th floor reshores
[6 empty] | 0.49727 |  |  |  |  | 12.4316
| 8 | 1.4973 | 0 | 1.4973 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1 | 0.025 | 1.025 |  |  |  |  | 7
[6 empty] | 0.075 |  |  |  |  | 1.875
| 6 | 1.05 | 0.025 | 1.075 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
10 - A | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Place 10th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 9 | 0.60273 | 0.4 | 1.0027 |  |  |  |  | 9
[6 empty] | 1.6973 |  |  |  |  | 42.4316
| 8 | 1.4973 | 0.4 | 1.8973 |  |  |  |  | 8
[6 empty] | 0.85 |  |  |  |  | 21.25
| 7 | 1.025 | 0.4 | 1.425 |  |  |  |  | 7
[6 empty] | 0.475 |  |  |  |  | 11.875
| 6 | 1.075 | 0.4 | 1.475 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - B | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Remove live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 9 | 1.0027 | -0.125 | 0.87773 |  |  |  |  | 9
[6 empty] | 1.3223 |  |  |  |  | 33.0566
| 8 | 1.8973 | -0.125 | 1.7723 |  |  |  |  | 8
[6 empty] | 0.6 |  |  |  |  | 15
| 7 | 1.425 | -0.125 | 1.3 |  |  |  |  | 7
[6 empty] | 0.35 |  |  |  |  | 8.75
| 6 | 1.475 | -0.125 | 1.35 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - C | 10 | 0 | 0.61113 | 0.61113 |  |  |  |  | 10 | Remove 9th floor shores
[6 empty] | 0.48887 |  |  |  |  | 12.2217
| 9 | 0.87773 | 0.61113 | 1.4889 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1.7723 | -0.77227 | 1 |  |  |  |  | 8
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.3 | -0.25 | 1.05 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.35 | -0.3 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - D | 10 | 0.61113 | 0 | 0.61113 |  |  |  |  | 10 | Remove 7th floor reshores
[6 empty] | 0.48887 |  |  |  |  | 12.2217
| 9 | 1.4889 | 0 | 1.4889 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1 | 0 | 1 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.05 | 0 | 1.05 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.05 | -0.05 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - E | 10 | 0.61113 | 0 | 0.61113 |  |  |  |  | 10 | Remove 9th floor shores
[6 empty] | 0.48887 |  |  |  |  | 12.2217
| 9 | 1.4889 | 0 | 1.4889 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1 | 0 | 1 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.05 | -0.05 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - F | 10 | 0.61113 | 0.38887 | 1 |  |  |  |  | 10 | Remove 10th floor shores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1.4889 | -0.48887 | 1 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1 | 0 | 1 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0

## AutoReshore 3DS
SHORING AND RESHORING ANALYSIS - ACI SP-4 METHOD - AutoReshore 3DS
Version 1.1
INPUTS |  |  | Panel Sets |  | 1
| Shore sets |  | 1 |  | Reshore sets |  | 2
| Shore spacing |  |  |  | Reshore spacing |  |  | Analysis ID
| N-S | 5 |  |  | N-S | 5 |  | 2014-10-01
| E-W | 5 |  |  | E-W | 5
| Area | 25 |  |  | Area | 25
[5 empty] | Load Factor | Area Load
| Fresh slab weight |  |  |  | 1 | 1 | 1
| Cured slab weight |  |  |  | 1 | 1 | 1
| Reinforcing/misc |  |  |  | 1 | 0.1 | 0.1
| Panel weight |  |  |  | 1 | 0.05 | 0.05
| Shore weight |  |  |  | 1 | 0.05 | 0.05
| Placing live load |  |  |  | 1 | 0.5 | 0.5
| Forming live load |  |  |  | 1 | 0.2 | 0.2
| Reshore weight |  |  |  | 1 | 0.05 | 0.05
Step # | Slab # | Load carried by slab |  |  | Unit load carried by shore | [5 empty] | Total individual shore load
|  | beginning | during | end |  | end of operation |  |  |  |  | end of operation
1 - A | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Set up 1st floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
1 - B | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
1 - C | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Place 1st floor slab
[6 empty] | 1.6 |  |  |  |  | 40
1 - D | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Remove 1st floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
1 - E | 1 | 0 | 0 | 0 |  |  |  |  | 1 | Remove 1st floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
2 - A | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Set up 2nd floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 1 | 0 | 0 | 0 |  |  |  |  | 1
[6 empty] | 1.45 |  |  |  |  | 36.25
2 - B | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 1 | 0 | 0 | 0 |  |  |  |  | 1
[6 empty] | 1.25 |  |  |  |  | 31.25
2 - C | 2 | 0 | 0 | 0 | [5 empty] | Activate 1st floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 1 | 0 | 1.2 | 1.2
[6 empty] | 0.05 |  |  |  |  | 1.25
2 - D | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Place 2nd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 1 | 1.2 | 0 | 1.2 |  |  |  |  | 1
[6 empty] | 1.45 |  |  |  |  | 36.25
2 - E | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Remove 2nd floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 1 | 1.2 | 0 | 1.2 |  |  |  |  | 1
[6 empty] | 0.95 |  |  |  |  | 23.75
2 - F | 2 | 0 | 0 | 0 |  |  |  |  | 2 | Remove 2nd floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 1 | 1.2 | 0 | 1.2 |  |  |  |  | 1
[6 empty] | 0.9 |  |  |  |  | 22.5
3 - A | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Set up 3rd floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 2 | 0 | 0 | 0 |  |  |  |  | 2
[6 empty] | 1.45 |  |  |  |  | 36.25
| 1 | 1.2 | 0 | 1.2 |  |  |  |  | 1
[6 empty] | 1.3 |  |  |  |  | 32.5
3 - B | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 2 | 0 | 0 | 0 |  |  |  |  | 2
[6 empty] | 1.25 |  |  |  |  | 31.25
| 1 | 1.2 | 0 | 1.2 |  |  |  |  | 1
[6 empty] | 1.1 |  |  |  |  | 27.5
3 - C | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Activate 2nd floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 2 | 0 | 1.2 | 1.2 |  |  |  |  | 2
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1.2 | -0.15 | 1.05 |  |  |  |  | 1
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
3 - D | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Place 3rd floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 2 | 1.2 | 0 | 1.2 |  |  |  |  | 2
[6 empty] | 1.45 |  |  |  |  | 36.25
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 1.45 |  |  |  |  | 36.25
3 - E | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Remove 3rd floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 2 | 1.2 | 0 | 1.2 |  |  |  |  | 2
[6 empty] | 0.95 |  |  |  |  | 23.75
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 0.95 |  |  |  |  | 23.75
3 - F | 3 | 0 | 0 | 0 |  |  |  |  | 3 | Remove 3rd floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 2 | 1.2 | 0 | 1.2 |  |  |  |  | 2
[6 empty] | 0.9 |  |  |  |  | 22.5
| 1 | 1.05 | 0 | 1.05 |  |  |  |  | 1
[6 empty] | 0.9 |  |  |  |  | 22.5
3 - G | 3 | 0 | 0.28333 | 0.28333 |  |  |  |  | 3 | Remove 1st floor reshores
[6 empty] | 0.76667 |  |  |  |  | 19.1667
| 2 | 1.2 | 0.28333 | 1.4833 |  |  |  |  | 2
[6 empty] | 0.33333 |  |  |  |  | 8.3333
| 1 | 1.05 | 0.28333 | 1.3333 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - A | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Set up 4th floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 3 | 0.28333 | 0.13333 | 0.41667 |  |  |  |  | 3
[6 empty] | 1.0333 |  |  |  |  | 25.8333
| 2 | 1.4833 | 0.13333 | 1.6167 |  |  |  |  | 2
[6 empty] | 0.46667 |  |  |  |  | 11.6667
| 1 | 1.3333 | 0.13333 | 1.4667 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - B | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 3 | 0.41667 | -0.066667 | 0.35 |  |  |  |  | 3
[6 empty] | 0.9 |  |  |  |  | 22.5
| 2 | 1.6167 | -0.066667 | 1.55 |  |  |  |  | 2
[6 empty] | 0.4 |  |  |  |  | 10
| 1 | 1.4667 | -0.066667 | 1.4 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - C | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Activate 3rd floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 3 | 0.35 | 0.85 | 1.2 |  |  |  |  | 3
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.55 | -0.5 | 1.05 |  |  |  |  | 2
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 1 | 1.4 | -0.35 | 1.05 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - D | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Place 4th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 3 | 1.2 | 0.46667 | 1.6667 |  |  |  |  | 3
[6 empty] | 0.98333 |  |  |  |  | 24.5833
| 2 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 2
[6 empty] | 0.51667 |  |  |  |  | 12.9167
| 1 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - E | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Remove 4th floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 3 | 1.6667 | -0.16667 | 1.5 |  |  |  |  | 3
[6 empty] | 0.65 |  |  |  |  | 16.25
| 2 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 2
[6 empty] | 0.35 |  |  |  |  | 8.75
| 1 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - F | 4 | 0 | 0 | 0 |  |  |  |  | 4 | Remove 4th floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 3 | 1.5 | -0.016667 | 1.4833 |  |  |  |  | 3
[6 empty] | 0.61667 |  |  |  |  | 15.4167
| 2 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 2
[6 empty] | 0.33333 |  |  |  |  | 8.3333
| 1 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
4 - G | 4 | 0 | 0.094444 | 0.094444 |  |  |  |  | 4 | Remove 2nd floor reshores
[6 empty] | 0.95556 |  |  |  |  | 23.8889
| 3 | 1.4833 | 0.094444 | 1.5778 |  |  |  |  | 3
[6 empty] | 0.42778 |  |  |  |  | 10.6944
| 2 | 1.3333 | 0.094444 | 1.4278 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1.3333 | -0.33333 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - A | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Set up 5th floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 4 | 0.094444 | 0.13333 | 0.22778 |  |  |  |  | 4
[6 empty] | 1.2222 |  |  |  |  | 30.5556
| 3 | 1.5778 | 0.13333 | 1.7111 |  |  |  |  | 3
[6 empty] | 0.56111 |  |  |  |  | 14.0278
| 2 | 1.4278 | 0.13333 | 1.5611 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - B | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 4 | 0.22778 | -0.066667 | 0.16111 |  |  |  |  | 4
[6 empty] | 1.0889 |  |  |  |  | 27.2222
| 3 | 1.7111 | -0.066667 | 1.6444 |  |  |  |  | 3
[6 empty] | 0.49444 |  |  |  |  | 12.3611
| 2 | 1.5611 | -0.066667 | 1.4944 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - C | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Activate 4th floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 4 | 0.16111 | 1.0389 | 1.2 |  |  |  |  | 4
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.6444 | -0.59444 | 1.05 |  |  |  |  | 3
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 2 | 1.4944 | -0.44444 | 1.05 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - D | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Place 5th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 4 | 1.2 | 0.46667 | 1.6667 |  |  |  |  | 4
[6 empty] | 0.98333 |  |  |  |  | 24.5833
| 3 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 3
[6 empty] | 0.51667 |  |  |  |  | 12.9167
| 2 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - E | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Remove 5th floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 4 | 1.6667 | -0.16667 | 1.5 |  |  |  |  | 4
[6 empty] | 0.65 |  |  |  |  | 16.25
| 3 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 3
[6 empty] | 0.35 |  |  |  |  | 8.75
| 2 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - F | 5 | 0 | 0 | 0 |  |  |  |  | 5 | Remove 5th floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 4 | 1.5 | -0.016667 | 1.4833 |  |  |  |  | 4
[6 empty] | 0.61667 |  |  |  |  | 15.4167
| 3 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 3
[6 empty] | 0.33333 |  |  |  |  | 8.3333
| 2 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
5 - G | 5 | 0 | 0.094444 | 0.094444 |  |  |  |  | 5 | Remove 3rd floor reshores
[6 empty] | 0.95556 |  |  |  |  | 23.8889
| 4 | 1.4833 | 0.094444 | 1.5778 |  |  |  |  | 4
[6 empty] | 0.42778 |  |  |  |  | 10.6944
| 3 | 1.3333 | 0.094444 | 1.4278 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1.3333 | -0.33333 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
| 1 | 1 | 0 | 1 |  |  |  |  | 1
[6 empty] | 0 |  |  |  |  | 0
6 - A | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Set up 6th floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 5 | 0.094444 | 0.13333 | 0.22778 |  |  |  |  | 5
[6 empty] | 1.2222 |  |  |  |  | 30.5556
| 4 | 1.5778 | 0.13333 | 1.7111 |  |  |  |  | 4
[6 empty] | 0.56111 |  |  |  |  | 14.0278
| 3 | 1.4278 | 0.13333 | 1.5611 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - B | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 5 | 0.22778 | -0.066667 | 0.16111 |  |  |  |  | 5
[6 empty] | 1.0889 |  |  |  |  | 27.2222
| 4 | 1.7111 | -0.066667 | 1.6444 |  |  |  |  | 4
[6 empty] | 0.49444 |  |  |  |  | 12.3611
| 3 | 1.5611 | -0.066667 | 1.4944 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - C | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Activate 5th floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 5 | 0.16111 | 1.0389 | 1.2 |  |  |  |  | 5
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.6444 | -0.59444 | 1.05 |  |  |  |  | 4
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 3 | 1.4944 | -0.44444 | 1.05 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - D | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Place 6th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 5 | 1.2 | 0.46667 | 1.6667 |  |  |  |  | 5
[6 empty] | 0.98333 |  |  |  |  | 24.5833
| 4 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 4
[6 empty] | 0.51667 |  |  |  |  | 12.9167
| 3 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - E | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Remove 6th floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 5 | 1.6667 | -0.16667 | 1.5 |  |  |  |  | 5
[6 empty] | 0.65 |  |  |  |  | 16.25
| 4 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 4
[6 empty] | 0.35 |  |  |  |  | 8.75
| 3 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - F | 6 | 0 | 0 | 0 |  |  |  |  | 6 | Remove 6th floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 5 | 1.5 | -0.016667 | 1.4833 |  |  |  |  | 5
[6 empty] | 0.61667 |  |  |  |  | 15.4167
| 4 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 4
[6 empty] | 0.33333 |  |  |  |  | 8.3333
| 3 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
6 - G | 6 | 0 | 0.094444 | 0.094444 |  |  |  |  | 6 | Remove 4th floor reshores
[6 empty] | 0.95556 |  |  |  |  | 23.8889
| 5 | 1.4833 | 0.094444 | 1.5778 |  |  |  |  | 5
[6 empty] | 0.42778 |  |  |  |  | 10.6944
| 4 | 1.3333 | 0.094444 | 1.4278 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1.3333 | -0.33333 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
| 2 | 1 | 0 | 1 |  |  |  |  | 2
[6 empty] | 0 |  |  |  |  | 0
7 - A | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Set up 7th floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 6 | 0.094444 | 0.13333 | 0.22778 |  |  |  |  | 6
[6 empty] | 1.2222 |  |  |  |  | 30.5556
| 5 | 1.5778 | 0.13333 | 1.7111 |  |  |  |  | 5
[6 empty] | 0.56111 |  |  |  |  | 14.0278
| 4 | 1.4278 | 0.13333 | 1.5611 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - B | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 6 | 0.22778 | -0.066667 | 0.16111 |  |  |  |  | 6
[6 empty] | 1.0889 |  |  |  |  | 27.2222
| 5 | 1.7111 | -0.066667 | 1.6444 |  |  |  |  | 5
[6 empty] | 0.49444 |  |  |  |  | 12.3611
| 4 | 1.5611 | -0.066667 | 1.4944 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - C | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Activate 6th floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 6 | 0.16111 | 1.0389 | 1.2 |  |  |  |  | 6
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.6444 | -0.59444 | 1.05 |  |  |  |  | 5
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 4 | 1.4944 | -0.44444 | 1.05 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - D | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Place 7th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 6 | 1.2 | 0.46667 | 1.6667 |  |  |  |  | 6
[6 empty] | 0.98333 |  |  |  |  | 24.5833
| 5 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 5
[6 empty] | 0.51667 |  |  |  |  | 12.9167
| 4 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - E | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Remove Placing Live Load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 6 | 1.6667 | -0.16667 | 1.5 |  |  |  |  | 6
[6 empty] | 0.65 |  |  |  |  | 16.25
| 5 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 5
[6 empty] | 0.35 |  |  |  |  | 8.75
| 4 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - F | 7 | 0 | 0 | 0 |  |  |  |  | 7 | Remove 7th floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 6 | 1.5 | -0.016667 | 1.4833 |  |  |  |  | 6
[6 empty] | 0.61667 |  |  |  |  | 15.4167
| 5 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 5
[6 empty] | 0.33333 |  |  |  |  | 8.3333
| 4 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
7 - G | 7 | 0 | 0.094444 | 0.094444 |  |  |  |  | 7 | Remove 5th floor reshores
[6 empty] | 0.95556 |  |  |  |  | 23.8889
| 6 | 1.4833 | 0.094444 | 1.5778 |  |  |  |  | 6
[6 empty] | 0.42778 |  |  |  |  | 10.6944
| 5 | 1.3333 | 0.094444 | 1.4278 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1.3333 | -0.33333 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
| 3 | 1 | 0 | 1 |  |  |  |  | 3
[6 empty] | 0 |  |  |  |  | 0
8 - A | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Set up 8th floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 7 | 0.094444 | 0.13333 | 0.22778 |  |  |  |  | 7
[6 empty] | 1.2222 |  |  |  |  | 30.5556
| 6 | 1.5778 | 0.13333 | 1.7111 |  |  |  |  | 6
[6 empty] | 0.56111 |  |  |  |  | 14.0278
| 5 | 1.4278 | 0.13333 | 1.5611 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - B | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 7 | 0.22778 | -0.066667 | 0.16111 |  |  |  |  | 7
[6 empty] | 1.0889 |  |  |  |  | 27.2222
| 6 | 1.7111 | -0.066667 | 1.6444 |  |  |  |  | 6
[6 empty] | 0.49444 |  |  |  |  | 12.3611
| 5 | 1.5611 | -0.066667 | 1.4944 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - C | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Activate 7th floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 7 | 0.16111 | 1.0389 | 1.2 |  |  |  |  | 7
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.6444 | -0.59444 | 1.05 |  |  |  |  | 6
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 5 | 1.4944 | -0.44444 | 1.05 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - D | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Place 8th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 7 | 1.2 | 0.46667 | 1.6667 |  |  |  |  | 7
[6 empty] | 0.98333 |  |  |  |  | 24.5833
| 6 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 6
[6 empty] | 0.51667 |  |  |  |  | 12.9167
| 5 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - E | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Remove 8th floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 7 | 1.6667 | -0.16667 | 1.5 |  |  |  |  | 7
[6 empty] | 0.65 |  |  |  |  | 16.25
| 6 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 6
[6 empty] | 0.35 |  |  |  |  | 8.75
| 5 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - F | 8 | 0 | 0 | 0 |  |  |  |  | 8 | Remove 8th floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 7 | 1.5 | -0.016667 | 1.4833 |  |  |  |  | 7
[6 empty] | 0.61667 |  |  |  |  | 15.4167
| 6 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 6
[6 empty] | 0.33333 |  |  |  |  | 8.3333
| 5 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
8 - G | 8 | 0 | 0.094444 | 0.094444 |  |  |  |  | 8 | Remove 6th floor reshores
[6 empty] | 0.95556 |  |  |  |  | 23.8889
| 7 | 1.4833 | 0.094444 | 1.5778 |  |  |  |  | 7
[6 empty] | 0.42778 |  |  |  |  | 10.6944
| 6 | 1.3333 | 0.094444 | 1.4278 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1.3333 | -0.33333 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
| 4 | 1 | 0 | 1 |  |  |  |  | 4
[6 empty] | 0 |  |  |  |  | 0
9 - A | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Set up 9th floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 8 | 0.094444 | 0.13333 | 0.22778 |  |  |  |  | 8
[6 empty] | 1.2222 |  |  |  |  | 30.5556
| 7 | 1.5778 | 0.13333 | 1.7111 |  |  |  |  | 7
[6 empty] | 0.56111 |  |  |  |  | 14.0278
| 6 | 1.4278 | 0.13333 | 1.5611 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - B | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 8 | 0.22778 | -0.066667 | 0.16111 |  |  |  |  | 8
[6 empty] | 1.0889 |  |  |  |  | 27.2222
| 7 | 1.7111 | -0.066667 | 1.6444 |  |  |  |  | 7
[6 empty] | 0.49444 |  |  |  |  | 12.3611
| 6 | 1.5611 | -0.066667 | 1.4944 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - C | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Activate 8th floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 8 | 0.16111 | 1.0389 | 1.2 |  |  |  |  | 8
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.6444 | -0.59444 | 1.05 |  |  |  |  | 7
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 6 | 1.4944 | -0.44444 | 1.05 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - D | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Place 9th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 8 | 1.2 | 0.46667 | 1.6667 |  |  |  |  | 8
[6 empty] | 0.98333 |  |  |  |  | 24.5833
| 7 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 7
[6 empty] | 0.51667 |  |  |  |  | 12.9167
| 6 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - E | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Remove 9th floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 8 | 1.6667 | -0.16667 | 1.5 |  |  |  |  | 8
[6 empty] | 0.65 |  |  |  |  | 16.25
| 7 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 7
[6 empty] | 0.35 |  |  |  |  | 8.75
| 6 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - F | 9 | 0 | 0 | 0 |  |  |  |  | 9 | Remove 9th floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 8 | 1.5 | -0.016667 | 1.4833 |  |  |  |  | 8
[6 empty] | 0.61667 |  |  |  |  | 15.4167
| 7 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 7
[6 empty] | 0.33333 |  |  |  |  | 8.3333
| 6 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
9 - G | 9 | 0 | 0.094444 | 0.094444 |  |  |  |  | 9 | Remove 7th floor reshores
[6 empty] | 0.95556 |  |  |  |  | 23.8889
| 8 | 1.4833 | 0.094444 | 1.5778 |  |  |  |  | 8
[6 empty] | 0.42778 |  |  |  |  | 10.6944
| 7 | 1.3333 | 0.094444 | 1.4278 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1.3333 | -0.33333 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
| 5 | 1 | 0 | 1 |  |  |  |  | 5
[6 empty] | 0 |  |  |  |  | 0
10 - A | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Set up 10th floor panels/shores/reinf'
[6 empty] | 0.4 |  |  |  |  | 10
| 9 | 0.094444 | 0.13333 | 0.22778 |  |  |  |  | 9
[6 empty] | 1.2222 |  |  |  |  | 30.5556
| 8 | 1.5778 | 0.13333 | 1.7111 |  |  |  |  | 8
[6 empty] | 0.56111 |  |  |  |  | 14.0278
| 7 | 1.4278 | 0.13333 | 1.5611 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - B | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Remove forming live load
[6 empty] | 0.2 |  |  |  |  | 5
| 9 | 0.22778 | -0.066667 | 0.16111 |  |  |  |  | 9
[6 empty] | 1.0889 |  |  |  |  | 27.2222
| 8 | 1.7111 | -0.066667 | 1.6444 |  |  |  |  | 8
[6 empty] | 0.49444 |  |  |  |  | 12.3611
| 7 | 1.5611 | -0.066667 | 1.4944 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - C | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Activate 9th floor - Resnug shores
[6 empty] | 0.2 |  |  |  |  | 5
| 9 | 0.16111 | 1.0389 | 1.2 |  |  |  |  | 9
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1.6444 | -0.59444 | 1.05 |  |  |  |  | 8
Resnug reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 7 | 1.4944 | -0.44444 | 1.05 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - D | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Place 10th floor slab
[6 empty] | 1.6 |  |  |  |  | 40
| 9 | 1.2 | 0.46667 | 1.6667 |  |  |  |  | 9
[6 empty] | 0.98333 |  |  |  |  | 24.5833
| 8 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 8
[6 empty] | 0.51667 |  |  |  |  | 12.9167
| 7 | 1.05 | 0.46667 | 1.5167 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - E | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Remove 10th floor live load
[6 empty] | 1.1 |  |  |  |  | 27.5
| 9 | 1.6667 | -0.16667 | 1.5 |  |  |  |  | 9
[6 empty] | 0.65 |  |  |  |  | 16.25
| 8 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 8
[6 empty] | 0.35 |  |  |  |  | 8.75
| 7 | 1.5167 | -0.16667 | 1.35 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - F | 10 | 0 | 0 | 0 |  |  |  |  | 10 | Remove 10th floor panels
[6 empty] | 1.05 |  |  |  |  | 26.25
| 9 | 1.5 | -0.016667 | 1.4833 |  |  |  |  | 9
[6 empty] | 0.61667 |  |  |  |  | 15.4167
| 8 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 8
[6 empty] | 0.33333 |  |  |  |  | 8.3333
| 7 | 1.35 | -0.016667 | 1.3333 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - G | 10 | 0 | 0.094444 | 0.094444 |  |  |  |  | 10 | Remove 8th floor reshores
[6 empty] | 0.95556 |  |  |  |  | 23.8889
| 9 | 1.4833 | 0.094444 | 1.5778 |  |  |  |  | 9
[6 empty] | 0.42778 |  |  |  |  | 10.6944
| 8 | 1.3333 | 0.094444 | 1.4278 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1.3333 | -0.33333 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - H | 10 | 0.094444 | 0.90556 | 1 |  |  |  |  | 10 | Activate 10th floor - Lower Drop Heads
[6 empty] | 0.05 |  |  |  |  | 1.25
| 9 | 1.5778 | -0.52778 | 1.05 |  |  |  |  | 9
[6 empty] | 0.05 |  |  |  |  | 1.25
| 8 | 1.4278 | -0.37778 | 1.05 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - I | 10 | 1 | 0 | 1 |  |  |  |  | 10 | Remove 9th floor reshores
[6 empty] | 0.05 |  |  |  |  | 1.25
| 9 | 1.05 | 0 | 1.05 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1.05 | -0.05 | 1 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0
10 - J | 10 | 1 | 0 | 1 |  |  |  |  | 10 | Remove 10th floor reshores
[6 empty] | 0 |  |  |  |  | 0
| 9 | 1.05 | -0.05 | 1 |  |  |  |  | 9
[6 empty] | 0 |  |  |  |  | 0
| 8 | 1 | 0 | 1 |  |  |  |  | 8
[6 empty] | 0 |  |  |  |  | 0
| 7 | 1 | 0 | 1 |  |  |  |  | 7
[6 empty] | 0 |  |  |  |  | 0
| 6 | 1 | 0 | 1 |  |  |  |  | 6
[6 empty] | 0 |  |  |  |  | 0